## Status
S.No | Project Name | LOT ID | Work Order | PROJECT NAME | PO QUANTITY | Lot Start Qty | Lot end Qty | SMT Yield | TLA Yield | Overall Yield | Units used for setup | SMT Rejects | TLA Rejects | SMT Reject breakdown | TLA Reject breakdown | Lot start date | Lot end date | SMT Cycle time (%) | TLA Cycle time (%) | QUANTITY | PROGRESS | PO NUMBER | PO Date | ASSEMBLY REPORT STATUS | REPORT PREPARED BY | REMARKS | REMARKS | BUILD | CUSTOMER | SHIPPED QUANTITY | STORED NUMBER | CONSUMED NUMBER | REJECT NUMBER | GRR for ICT | UNCONSUMED | SHIPPED DATE | STATUS OF PANEL |  | Shipment For
1 |  | T-GB-202419001 |  | Glove Box | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | N.A | 40 | TO BE SCRAPPED |  |  | NA |  | Without N2 flow | Without N2 flow | SAMPLE | TAPTI | [7 empty] | 2 Panels, 2 PCB BGA bridging
2 |  | T-GB-202419002 |  | Glove Box | 60 |  | -10 |  |  | #DIV/0! | 5 | 5 | 5 | [5 empty] | N.A | 60 | Shipped Out |  |  | COMPLETED | SANTHOSH | Possible RF cover liftoff | Possible RF cover liftoff | ENGINEERING | TAPTI
3 |  | T-UD-202419001 |  | USB DUO | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | N.A | 40 | TO BE SCRAPPED |  |  | NA |  | Without N2 flow | Without N2 flow | SAMPLE | TAPTI | [7 empty] | Without laser Marking
4 |  | T-UD-202419002 |  | USB DUO | 60 |  | -10 |  |  | #DIV/0! | 5 | 5 | 5 | [5 empty] | N.A | 60 | Shipped Out |  |  | COMPLETED | SANTHOSH | Reflow oven issues, caused damage of connectors | Reflow oven issues, caused damage of connectors | ENGINEERING | TAPTI | [7 empty] | 40 PCB are okay and 1 panel was damaged during reflow oven.
5 |  | T-VC-202419001 |  | VC USB | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | N.A | 8/32 | AOI |  |  | NA |  | Capacitor lift off by 200um due to glue. | Capacitor lift off by 200um due to glue. | ENGINEERING | TAPTI | [7 empty] | 4 Panel bottom done, 1 top done and rest need to be done
6 |  | T-VC-202420002 |  | VC USB | 8 |  | -10 |  |  | #DIV/0! | 5 | 5 | 5 | [5 empty] | N.A | 8/32 | Shipped Out |  |  | COMPLETED | SANTHOSH | Testing is completed and manual TLA, 1 Panel Bottom is mounted and not used for top. | Testing is completed and manual TLA, 1 Panel Bottom is mounted and not used for top. | ENGINEERING | TAPTI | [7 empty] | Rest 2 panel Bottom is performed, After correcting the polarity | 5 VC USB Assembled
7 |  | T-AA-202420001 |  | Audio Amplifier | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | N.A | 50 | PRODUCTION LOT |  |  | NA |  | 18 With Production, 20 Sent TLA NOAH, 12 Testing | 18 With Production, 20 Sent TLA NOAH, 12 Testing | SAMPLE | TAPTI
8 |  | T-UD-202422001 |  | USB DUO | 190 | 190 | 190 | 100% | 100% | 100% | 0 | 0 | 0 | NA | NA | 4th June 2024 | 7th June 2024 | 100% | N.A | 190 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | SANTHOSH |  |  | NPI | TAPTI | [7 empty] | Products are shipped already
9 |  | T-GB-202424001 |  | GLOVE BOX | 50 | 52 | 52 | 100% | 100% | 100% | 2 | 0 | 0 | NA | NA | 6th June 2024 | 26th June 2024 | 100% | 150% | 52 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | SANTHOSH | Label Design Approval delayed by the Customer | Product shipped out, Reports compilation in progress | NPI | TAPTI | [6 empty] | 2024-06-27 | Need help to replace labels
10 |  | T-VC-202425001 |  | VC USB | 50 | 120 | 104 | 86.7% | 100% | 86.67% | 58 | 16 | 0 | 8x IC reverse Polarity - Pick and Place 1x Open Lead in IC - X-ray 3x IC Pin Liftoff - ICT 2x Dioide short 2x Short in Board | 34x Used for Setup | 20th June 2024 | 27th June 2024 | 120% | 100% | 120 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | SANTHOSH | Vaccum reflow issues, N2 inconsistency, Solved | TLA buy off completed, Product Shipped out, Reports compilation in progress | NPI | TAPTI |  | 3 |  |  |  |  | 2024-06-29 | 4 Panel stored in Locker, 1 gave to Prince for Display, 3 remaining
11 |  | T-GB-202424002 |  | GLOVE BOX | 10 | 12 | 12 | 100% | 100% | 100% | 2 | 0 | 0 | NA | NA | 25th July 2024 | 3rd August 2024 | 100% | 100% | 12 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | SANTHOSH |  | Many Problems in TLA machine, all addressed | NPI | TAPTI | Stored in locker FG | 2 |  |  |  |  | 2024-08-05 | Completed, 2 Golden Sample, 2 Rejects
12 |  | T-BM-202431101 |  | BMB-Model 1 | 15 | 60 | 59 | 98.33% | NA | 98.33% | 21 | 1 | 0 | 1x Inconsisten coating coverage | NA | 12th August 2024 | 23rd August 2024 | 130% | N.A | 60 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | HARI | Setup for Conformal Coating, AOI - Conformal Coating | 38 Good Boards, 15 for Shipment | TQP | TAPTI | 15 | 28 | [5 empty] | Stored in PCBA Line
13 |  | T-BM-202431201 |  | BMB-Model 2 | 15 | 63 | 55 | 87.3% | NA | 87.3% | 16 | 8 | 0 | 1 x Improper Kepton Tape 3x Coating on Kepton Tape 3x Laser Marking MES issue 1x Component Offset | NA | 12th August 2024 | 23rd August 2024 | 130% | N.A | 63 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | HARI | Setup for Conformal Coating, AOI - Conformal Coating | 38 Good Boards, 15 for Shipment | TQP | TAPTI | 15 | 28 | [5 empty] | Stored in PCBA Line
14 |  | T-BM-202431301 |  | BMB-Model 3 | 15 | 60 | 52 | 86.67% | NA | 86.67% | 0 | 8 | 0 | 8x Bad coating coverage | NA | 12th August 2024 | 23rd August 2024 | 130% | N.A | 60 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | HARI | Setup for Conformal Coating, AOI - Conformal Coating | 19 Good Boards, 15 for Shipment | TQP | TAPTI | 15 | 9 | [5 empty] | Stored in PCBA Line
15 |  | T-BM-202431401 |  | BMB-Model 4 | 15 | 21 | 21 | 100% | NA | 100% | 0 | 0 | 0 | NA | NA | 12th August 2024 | 23rd August 2024 | 130% | N.A | 60 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | HARI | Setup for Conformal Coating, AOI - Conformal Coating | 21 Good Boards, 15 for Shipment | TQP | TAPTI | 15 | 11 | [5 empty] | Stored in PCBA Line
16 |  | T-GB-202434001 |  | GLOVE BOX | 37 | 60 | 58 | 96.67% | 100% | 96.67% | 20 | 2 | 0 | NA | NA | 23rd August 2024 | 17th Sept 2024 | 100% | 100% | 60 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | PRADEEP |  | TLA, Label Offset observed, Waiting for internal confirmation. New pcb are used for 11 defective sample, 1 damage in cable , out of 12 new pcb. | PV1 | TAPTI |  | 1
17 |  | TE-LN-202435001 |  | LNA | 9 | 10 | 9 | 90% | NA | 90% | 0 | 1 | 0 | 1x Pick and Place drop issue | NA | 30th August 2024 | 23rd Sept 2024 | 100% | 100% | 9 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | HARI - report, Santhosh - laser | Laser Marking approval from the customer is delayed | Short of Components Cap, inductor and resistor, due to pick and place issue. Waiting for confirmation for laser marking. | NPI | TEJAS | 9
17 |  | T-GB-202424003 |  | GLOVE BOX | 34 | 60 | 52 | 90% | 96.3% | 86.67% | 20 | 6 | 2 | 4x ICT Failure 1x USB Connector missing 1 ICT and AXI Failure | 1x Improper Screwing 1x Label Printing NG | 30th August 2024 | 5th Sept 2024 | 100% | 120% | 60 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | SANTHOSH | TLA machine cable issue and label positioning issue, solved | Routing Completed, 34 Boards Okay, 6 NG, 1 AXI, 3 ICT, 1 ICT and AXI, 1 USB Missing | NPI | TAPTI | 30 | 4 |  |  |  |  | 2024-05-09
18 |  | T-UD-202435001 |  | USB DUO | 47 | 54 | 47 | 87% | NA | 87.04% | 0 | 7 | 0 | 7x Connector damage due to Routing fixture | NA | 9th Sept 2024 | 18th Sept 2024 | 100% | N.A | 54 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | APARNA | Delayed in Modifying pallete for USB DUO routing fixtures | Laser Marking, Pick and place calibration, AOI setup all delayed. Testing all passed, OQC needs to be done. USB Duo, Routing fixture has damaged components, modified fixtures and re routing again. Needed to check the USB Duo foam trays as there were placement issues. | PV1 | TAPTI | 47 | 6, 1 given for Sriram |  | 7 |  |  | 2024-09-30 | Stored near Washing
19 |  | T-VC-202436001 |  | VC USB | 36 | 64 | 45 | 70.31% | 95.74% | 70.31% | 0 | 17 | 2 | NA | 1x Shield Frame damage 1x Cpacitor Offset | 6th Sept 2024 | 14th Sept 2024 | 100% | 100% | 64 | Shipped Out |  |  | PENDING | HARI |  | VCUSB 23 rejects and trying to get good boards from ICT, 6 panels already depanelled. TLA completed, partially with MES. All testing passed and Sent for Packing after OQC | PV1 | TAPTI | ICT-holding | 45
20 |  | T-GB-202437001 |  | GLOVE BOX | 300 | 400 | 340 | 96.5% | 88.08% | 85% | 169 | 14 | 46 | ICT - 11 Short/ Failure AXI - 3 BGA Short | TLA - MES, Testing Failure - 137 | 6th Sept 2024 | 1st October 2024 | 100% | 200% | 400 | Shipped Out |  |  | COMPLETED, WAITING FOR SIGN | SANTHOSH | Customer Visit and TQP documents approval dalyed. Shipment Done. | Bottom side placement and AOI completed, Top side SPP is beign performed. Top side completed , AXI, Testing also completed, 389 pass. 30+30+30+50 Run front of customer. Remaining to be sent. Waiting FOR Customer approval. | TQP | TAPTI |  | 87 |  | 14 |  | 24 | 5th October
26 |  | T-GB-202439001 |  | GLOVE BOX |  | 200 | 170 | 93% | 91.4% | 85% |  | 14 | 16 | ICT - 3 Failure Laser - 1 Offset Excess Solder - 10 SPI |  | 28th Sept 2024 | 1st October 2024 | 100% | 200% | 200 | Shipped Out |  |  |  | SANTHOSH |  | TLA Line Approval, as there is change in Sensor orientation. | TQP | TAPTI |  |  |  | 14 |  |  | 5th October |  |  |  | 5th October
21 |  | T-VC-202437001 |  | VC USB | 95 | 300 | 269 | 96.67% | 92.76% | 89.67% | 36 | 10 | 21 | NA | NA | 6th Sept 2024 | 9th October 2024 | 100% | 200% |  | Shipped Out |  |  | PENDING | PRADEEP | ICT Tester had some relay issues, Then later repaired. | Bottom side completed, Top Needs to start. SMT and Testing completed, TLA 36 used, 25 Good out of 33, 3 used for setup. 54 boards okay, needed 95 | TQP | TAPTI | 95-To be packed | 1-Golden | 135-given/117-consumed/96-good/21-rejects | 24+21 |  | 82 | 10th October |  |  |  | 10th October
22 |  | T-BM-202438101 |  | BMB-Model 1 | 8 | 27 | 27 | 100% | NA | 100% | 19 | 0 | 0 | 3 Boards AOI Kapp 3 Boards AXI 10 Boards for Gauge R&R 3 Boards for Conformal Coating | NA | 18th Sept 2024 | 23rd Sept 2024 | 100% | N.A | 30 | PACKED |  |  | COMPLETED, WAITING FOR SIGN | APARNA |  | Equipment problem in ICT. Conformal Coating issue. Bottom side impressions are found. | TQP 2 | TAPTI |  | 8 | [5 empty] | Stored in PCBA Line |  | Nevada, Salable build
23 |  | T-BM-202438201 |  | BMB-Model 2 | 8 | 27 | 27 | 100% | NA | 100% | 19 | 0 | 0 |  | NA | 18th Sept 2024 | 23rd Sept 2024 | 100% | N.A | 30 | PACKED |  |  | COMPLETED, WAITING FOR SIGN | APARNA |  |  | TQP 2 | TAPTI |  | 8 | [5 empty] | Stored in PCBA Line |  | Nevada, Salable build
24 |  | T-BM-202438301 |  | BMB-Model 3 | 8 | 27 | 27 | 100% | NA | 100% | 19 | 0 | 0 |  | NA | 18th Sept 2024 | 23rd Sept 2024 | 100% | N.A | 30 | PACKED |  |  | COMPLETED, WAITING FOR SIGN | APARNA |  |  | TQP 2 | TAPTI |  | 8 | [5 empty] | Stored in PCBA Line |  | Nevada, Salable build
25 |  | T-BM-202438401 |  | BMB-Model 4 | 8 | 27 | 27 | 100% | NA | 100% | 19 | 0 | 0 |  | NA | 18th Sept 2024 | 23rd Sept 2024 | 100% | N.A | 30 | PACKED |  |  | COMPLETED, WAITING FOR SIGN | APARNA |  | Line Approved and 300 samples produced - 04-10-2024,10:43 AM | TQP 2 | TAPTI |  | 8 | [5 empty] | Stored in PCBA Line |  | Nevada, Salable build
27 |  | T-BM-202439101 |  | BMB-Model 1 | 5 | 75 | 73 | 97.33% | NA | 97.33% | 0 | 2 | 0 | NA | NA | 24th SEPT 2024 | 30th Sept 2024 | 100% | N.A | 75 | Shipped Out |  |  | NO REPORT | NO REPORT |  | On hold till further instructions from customer, 2 Reject due to fingerprint impression. | PILOT | TAPTI |  |  |  | 2 |  |  |  | Stored in PCBA Line
28 |  | T-BM-202439201 |  | BMB-Model 2 | 5 | 75 | 71 | 94.67% | NA | 94.67% | 0 | 4 | 0 | NA | NA | 24th SEPT 2024 | 30th Sept 2024 | 100% | N.A | 75 | Shipped Out |  |  | NO REPORT | NO REPORT |  | On hold till further instructions from customer, 4 Reject due to Not curing of conformal Coating. | PILOT | TAPTI |  |  |  | 4 |  |  |  | Stored in PCBA Line
29 |  | T-BM-202439301 |  | BMB-Model 3 | 5 | 75 | 75 | 100% | NA | 100% | 0 | 0 | 0 | NA | NA | 24th SEPT 2024 | 30th Sept 2024 | 100% | N.A | 75 | Shipped Out |  |  | NO REPORT | NO REPORT |  | On hold till further instructions from customer | PILOT | TAPTI | [7 empty] | Stored in PCBA Line
30 |  | T-BM-202439401 |  | BMB-Model 4 | 5 | 75 | 75 | 100% | NA | 100% | 0 | 0 | 0 | NA | NA | 24th SEPT 2024 | 30th Sept 2024 | 100% | N.A | 75 | Shipped Out |  |  | NO REPORT | NO REPORT |  | On hold till further instructions from customer | PILOT | TAPTI | [7 empty] | Stored in PCBA Line
31 |  | TM-M-202439001 |  | BMS MASTER | 23 | 23 | 23 | 100% | NA | 100% | 0 | 0 | 0 | NA | NA | 4th October 2024 | In Progress | 100% | N.A | 23 | PACKED |  |  | PENDING | APARNA |  |  | NPI | TML
32 |  | TM-S-202439001 |  | BMS SLAVE | 26 | 26 | 26 | 100% | NA | 100% | 0 | 0 | 0 | NA | NA | 4th October 2024 | In Progress | 100% | N.A | 28 | PACKED |  |  | PENDING | PRADEEP |  |  | NPI | TML
33 |  | T-UD-202440001 |  | USB DUO | 926 | 972 | 902 | 92.28% | NA | 92.8% | 0 | 70 | 0 | 18x Board broken 5x Bridging - AOI 6x pick drop - AOI 29x Solder bridging - AXI 5x Excess void 7x ICT Mariginal failure in tolerance | 0 | 4th October 2024 | 11th October 2024 | 100% | N.A | 972 | PACKED |  |  | COMPLETED, WAITING FOR SIGN | SANTHOSH | 5 Units Pending for P.O |  | TQP | TAPTI | 100+650+95+5 | 104 +18(AOI KAPPA) |  |  |  |  | 15th October | 104 Units, MES failure and second time passed with reject (70)
34 |  | T-GB-202442001 |  | GLOVE BOX | 400 | 420 | 367 | 95.48% | 91.52% | 87.38% | 0 | 19 | 34 | 7x Missing Component 12x BGA Short | 18x Label Issue 16x MES Checkout Issue | 16th Ocotber 2024 |  | 100% |  |  | TLA |  |  | NO REPORT | NO REPORT |  |  | PILOT | TAPTI
35 |  | T-VC-202443001 |  | VC USB | 200 | 420 | 367 | 95.48% | 91.52% | 87.38% | 0 | 19 | 34 |  |  | 24th October 2024 |  | 100% |  | 200 | TO BE SCRAPPED |  |  | NA |  |  |  | PV1.5 | TAPTI
36 |  | T-UD-202443001 |  | USB DUO | 3600 | 3600 | 3600 | 100% | 100% | 100% | 0 |  |  |  |  | 26th October 2024 |  | 100% | N.A |  | AXI |  |  | NO REPORT | NO REPORT | IN PROGRESS |  | PILOT | TAPTI
37 |  | T-VC-202444001 |  | VC USB | 200 | 216 | 208 | 96.3% | 100% | 96.3% | 0 | 8 |  | 3x Scratch mark on PCB 2x solder smudging - Conveyer width issue, Disturbed while trying to fix the conveyer. 1x Solder paste bridging 2x Solder Bridging in USB |  | 28th October 2024 |  | 100% |  | 200 | AXI |  |  | BUILD IN PROGRESS | SANTHOSH | REBUILD FOR PREVIOUS ISSUE |  | PV1.5 | TAPTI
38 |  | JL-GD-202445001 |  | Gate Driver | 10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 6th Nov 2024 | 6th Nov 2024 | NA |  | 10 | TESTING |  |  | NO REPORT | NO REPORT | Only Testing |  | NPI TESTING | JLR | [7 empty] | PRODUCT PACKED BY SOMA |  | JLR
39 |  | T-UD-202448001 |  | USB DUO | 34 | 34 | 34 | 92.28% | NA | 100% | 0 | 0 | 0 |  |  | 29th November 2024 |  |  |  | 972 | NOT YET STARTED |  |  | BUILD IN PROGRESS | SANTHOSH |  |  | PV 2 | TAPTI | [6 empty] | 15th October | 104 Units, MES failure and second time passed with reject (70)
40 |  | T-GB-202449001 |  | GLOVE BOX | 51 | 60 | 60 | 100% | NA | 100% | 0 | 0 | 0 |  |  | 2nd December 2024 |  |  |  | 972 | NOT YET STARTED |  |  | BUILD IN PROGRESS | SANTHOSH |  |  | PV 2 | TAPTI | [6 empty] | 15th October | 104 Units, MES failure and second time passed with reject (70)
41 |  | T-HV-202449001 |  | HVAC |  |  | 0 | #DIV/0! | NA | #DIV/0! | 0 | 0 | 0 |  |  | 2nd December 2024 |  |  |  | 972 | NOT YET STARTED |  |  | BUILD IN PROGRESS | SANTHOSH |  |  | PV 2 | TAPTI | [6 empty] | 15th October | 104 Units, MES failure and second time passed with reject (70)
42 |  | T-HV-202449002 |  | HVAC |  |  | 0 | #DIV/0! | NA | #DIV/0! | 0 | 0 | 0 |  |  | 2nd December 2024 |  |  |  | 972 | NOT YET STARTED |  |  | BUILD IN PROGRESS | SANTHOSH |  |  | PV 2 | TAPTI | [6 empty] | 15th October | 104 Units, MES failure and second time passed with reject (70)
43 |  | T-GB-202507001 | 1776863-01-D_NPI_PV3 | GLOVEBOX | 66 | 80 | 60 | 75% | NA | 75% | 0 | 20 | 0 |  |  | 13th Februrary 2025 |  |  |  |  | ICT |  |  |  | SANTHOSH |  |  | PV3 | TAPTI
44 |  | T-UD-202507001 | 1861611-01-C_NPI_PV3 | USB DUO | 32 | 34 | 22 | 64.71% | NA | 64.71% | 0 | 12 | 0 | 9x Solder bridging/short 3x ICT Open | NA | 13th Februrary 2025 | 17th February 2025 | 100% | N.A | 36 | OQC |  |  |  | SANTHOSH |  |  | PV3 | TAPTI
45 |  | T-VC-202509001 | 1861596-40-C_NPI, 1855541-40-F_NPI | VCUSB | 110 | 200 | 164 | 85% | 96.47% | 82% |  | 30 | 6 | 25x ICT Failure 5x AXI NG | 4x Gasket placement failure 2x Screwing station NG | 20th February 2025 | 7th March 2025 | 100% | 100% |  |  |  |  | COMPLETED | SANTHOSH
46 |  | T-GB-202509001 | 1776863-02-D_NPI, 1771993-02-K_NPI | GLOVEBOX | 110 | 200 | 198 | 99.5% | 99.5% | 99% |  | 1 | 1 | Pick and Place Component Liftup | Cable damage | 20th February 2025 | 7th March 2025 | 100% | 100% |  |  |  |  | COMPLETED | SANTHOSH
47 |  | T-UD-202510001 | 1861611-01-C_PV3 | USB DUO | 29 | 36 | 29 | 80.56% | NA | 80.56% | 0 | 7 | 0 | 4 x Connector Fall down in Reflow(RMC) | NA | 2025-03-19 | 2025-03-19 | 100% | N.A | 36 | Shipped Out | 4701226640, 4701217827 | 04-03-2025, 26-02-2025 | COMPLETED | SANTHOSH |  |  | PV3 | TAPTI | 5 | [5 empty] | 2025-03-19 | Stored in Dry cabinet
48 | GLOVEBOX - PV3 Rebuild | T-GB-202513001 | 1776863-01-D_PV3, 1771993-00-K_PV3 | GLOVEBOX | 66 | 75 | 68 | 90.67% | 100% | 90.67% |  | 7 | 0 | 2x AXI reject- less solder paste on corners. 5x ICT Test reject. | Waiting for TLA | 2025-03-25 |  |  |  | 100 | 10 Shipped out |  |  |  | SANTHOSH |  |  | PV3 | TAPTI
49 | REPEATED | T-VC-202513001 | 1861596-13-C_PV2.5, 1855541-14-E_PV2.5 | VCUSB | 34 | 45 | 45 | 100% | 100% |  |  | 0 | 0 | 3x Skipped due to less components (Input is 45) | Waiting for TLA | 2025-03-25 |  |  |  | 90 | 30 Shipped out | 4701228436 | 2025-03-05 |  | SANTHOSH | IN FG STORES |  | PV2.5 | TAPTI
50 | AA-PV1 | T-AA-202511001 | #REF! | Audio Amplifier | #REF! | 92 | 82 | 98.91% | 82.69% | 81.79% | 17 | 1 | 9 | Component fall down - IC | 6x No screw 2x No label 1x MES timeout error -Noah machine | 2025-03-25 |  |  |  | 90 | 20 Shipped out |  |  |  | SANTHOSH | IN FG STORES |  | PV2.5 | TAPTI
51 | PV2.5 | #REF! | #REF! | VCUSB | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | 0 |  | Waiting for TLA | #REF! | #REF! |  |  |  |  | #REF! |  | COMPLETED | SANTHOSH | [5 empty] | 6x Panels are stored in Line 3 Magazines.
52 | VCUSB-E41-XQ-230 | T-VC-202515001 | 1861596-40-C_NPI_02, 1855541-40-F_NPI_02 | VCUSB | 230 | 200 | 181 | 97% | 93.3% | 90.5% | 18 | 6 | 13 | 1x AOI Component Tombstone - capacitor 5x ICT Failure. | 1x Label Position NG 1x Gasket position NG 11x Heat sink pasted with old Serial Number, 14-E, due to time constraint we couldn't use the board. | 07-04-2025 | 18-04-2025 |  |  | 192 |  | 4701228436 |  |  | SANTHOSH | Already Available quantity 100 |  |  |  |  | 32x Good FG are available in FG stores, 14x FG Units are stored (Unclassified) 2x Stored in Sub stores 2x OQC reject stores in substores |  |  |  |  | 2025-04-22
53 | GB-E41-PM-130 | T-GB-202516001 | 1776863-02-D_NPI_02, 1771993-02-K_NPI_02 | GLOVEBOX | 130 | 200 | 183 | 97.5% | 93.85% | 91.5% | 4 | 5 | 12 | 4x USB A Cover disturbed during scanning. 1x No Shield placed | 4x Screw NG 6x Cable Insertion Force NG 2x Label Pasting not done. | 19-04-2025 | 28-04-2025, Routing Completed, 5 defect in Bot, 1 in TOP |  |  |  |  | 4701291867 |  |  | SANTHOSH | [5 empty] | 46x PCBA Stored in Dry Cabinet 48x FG Stores in FG stores, Ground floor 20x NG FGs are stored in FG stores, Ground Floor
54 | AA-PV1-LOT-2 | T-AA-202519001 | , 4701364716 | Audio Amplifier | 14+6 | 40 | 28 | 70% | 100% | 70% |  | 12 | 0 | 1x 2 Pin SOD Lift Up 6x Cold Solder 4x Solder Paste time exceeded 2 hours. 1x Failure in AOI - 2 pin SOD Upside down. |  | 23-04-2025 | 03-05-2025 |  |  |  |  | 4701364716 |  |  | SANTHOSH
55 | BMB-M1-PRE-SOP | T-BM-202521101 | 1915616-01-C_NPI | BMB-M1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | 0 |  |  | #REF! | #REF! |  |  |  |  | #REF! |  |  | SANTHOSH
56 | BMB-M2-PRE-SOP | T-BM-202521201 | 1915617-01-C_NPI | BMB-M2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | 0 |  |  | #REF! | #REF! |  |  |  |  | #REF! |  |  | SANTHOSH
57 | BMB-M3-PRE-SOP | T-BM-202521301 | 1915618-01-C_NPI | BMB-M3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | 0 |  |  | #REF! | #REF! |  |  |  |  | #REF! |  |  | SANTHOSH
58 | BMB-M4-PRE-SOP | T-BM-202521401 | 1915619-01-C_NPI | BMB-M4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | 0 |  |  | #REF! | #REF! |  |  |  |  | #REF! |  |  | SANTHOSH
59 | GB-Shield Cover Validation | #REF! | #REF! | GLOVEBOX | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! |  |  |  |  | #REF! |  |  | SANTHOSH
60 | TQP-L3-40 | #REF! | #REF! | VCUSB | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! |  |  |  |  | #REF! |  |  | SANTHOSH
61 | UD-Reflow_L2 | #REF! | #REF! | USB DUO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! |  |  |  |  | #REF! |  |  | SANTHOSH

## TAPTI_Presentation
S.NO | LOT ID | PROJECT NAME | LINE NUMBER | PO QUANTITY | Lot Start Qty | Lot end Qty | SMT Yield | TLA Yield | Overall Yield | Units used for setup | SMT Rejects | TLA Rejects | SMT Reject breakdown | TLA Reject breakdown | Lot start date | Lot end date | Cycle time (%) | REMARKS | BUILD | CUSTOMER
1 | T-GB-202419001 | Glove Box | 1 | NA |  | -10 |  |  | 100% | 5 | 5 | 5 | [5 empty] | TO BE SCRAPPED | NA | TAPTI
2 | T-GB-202419002 | Glove Box | 1 | 60 |  | -10 |  |  | 100% | 5 | 5 | 5 | [5 empty] | Shipped Out | COMPLETED | TAPTI
3 | T-UD-202419001 | USB DUO | 1 | NA |  | -10 |  |  | 100% | 5 | 5 | 5 | [5 empty] | TO BE SCRAPPED | NA | TAPTI
4 | T-UD-202419002 | USB DUO | 1 | 60 |  | -10 |  |  | 100% | 5 | 5 | 5 | [5 empty] | Shipped Out | COMPLETED | TAPTI
5 | T-VC-202419001 | VCUSB | 1 | NA |  | -10 |  |  | 100% | 5 | 5 | 5 | [5 empty] | AOI | NA | TAPTI
6 | T-VC-202420002 | VCUSB | 1 | 8 |  | -10 |  |  | 100% | 5 | 5 | 5 | [5 empty] | Shipped Out | COMPLETED | TAPTI
7 | T-AA-202420001 | Audio Amplifier | 1 | 20 |  | -10 |  |  | 100% | 5 | 5 | 5 | [5 empty] | PRODUCTION LOT | NA | TAPTI
1 | T-UD-202422001 | USB DUO | 1 | 190 | 190 | 190 | 100% | 100% | 100% | 0 | 0 | 0 | NA | NA | 4th June 2024 | 7th June 2024 | 100% |  | NPI | TAPTI
2 | T-GB-202424001 | GLOVE BOX | 1 | 50 | 52 | 52 | 100% | 100% | 100% | 2 | 0 | 0 | NA | NA | 6th June 2024 | 26th June 2024 | 150% | Label Design Approval delayed by the Customer | NPI | TAPTI
3 | T-VC-202425001 | VCUSB | 1 | 50 | 120 | 104 | 86.7% | 100% | 86.67% | 58 | 16 | 0 | 8x IC reverse Polarity - Pick and Place 1x Open Lead in IC - X-ray 3x IC Pin Liftoff - ICT 2x Dioide short 2x Short in Board | 34x Used for Setup | 20th June 2024 | 27th June 2024 | 120% | Vaccum reflow issues, N2 inconsistency, Solved | NPI | TEJAS
4 | T-GB-202424002 | GLOVE BOX | 1 | 10 | 12 | 12 | 100% | 100% | 100% | 2 | 0 | 0 | NA | NA | 25th July 2024 | 3rd August 2024 | 100% |  | NPI | TAPTI
5 | T-BM-202431101 | BMB-Model 1 | 1 | 15 | 60 | 59 | 98.33% | NA | 98.33% | 21 | 1 | 0 | 1x Inconsisten coating coverage | NA | 12th August 2024 | 23rd August 2024 | 130% | Setup for Conformal Coating, AOI - Conformal Coating | TQP | TAPTI
6 | T-BM-202431201 | BMB-Model 2 | 1 | 15 | 63 | 55 | 87.3% | NA | 87.3% | 16 | 8 | 0 | 1 x Improper Kepton Tape 3x Coating on Kepton Tape 3x Laser Marking MES issue 1x Component Offset | NA | 12th August 2024 | 23rd August 2024 | 130% | Setup for Conformal Coating, AOI - Conformal Coating | TQP | TAPTI
7 | T-BM-202431301 | BMB-Model 3 | 1 | 15 | 60 | 52 | 86.67% | NA | 86.67% | 0 | 8 | 0 | 8x Bad coating coverage | NA | 12th August 2024 | 23rd August 2024 | 130% | Setup for Conformal Coating, AOI - Conformal Coating | TQP | TAPTI
8 | T-BM-202431401 | BMB-Model 4 | 1 | 15 | 21 | 21 | 100% | NA | 100% | 0 | 0 | 0 | NA | NA | 12th August 2024 | 23rd August 2024 | 130% | Setup for Conformal Coating, AOI - Conformal Coating | TQP | TAPTI
9 | T-GB-202434001 | GLOVE BOX | 1 | 37 | 60 | 58 | 96.67% | 100% | 96.67% | 20 | 2 | 0 | NA | NA | 23rd August 2024 | 17th Sept 2024 | 100% |  | PV1 | TAPTI
10 | TE-LN-202435001 | LNA | 1 | 9 | 10 | 9 | 90% | NA | 90% | 0 | 1 | 0 | 1x Pick and Place drop issue | NA | 30th August 2024 | 23rd Sept 2024 | 100% | Laser Marking approval from the customer is delayed | NPI | TAPTI
11 | T-GB-202424003 | GLOVE BOX | 1 | 34 | 60 | 52 | 90% | 96.3% | 86.67% | 20 | 6 | 2 | 4x ICT Failure 1x USB Connector missing 1 ICT and AXI Failure | 1x Improper Screwing 1x Label Printing NG | 30th August 2024 | 5th Sept 2024 | 120% | TLA machine cable issue and label positioning issue, solved | NPI | TAPTI
12 | T-UD-202435001 | USB DUO | 1 | 47 | 54 | 47 | 87% | NA | 87.04% | 0 | 7 | 0 | 7x Connector damage due to Routing fixture | NA | 9th Sept 2024 | 18th Sept 2024 | 130% | Delayed in Modifying pallete for USB DUO routing fixtures | PV1 | TAPTI
13 | T-VC-202436001 | VC USB | 1 | 36 | 64 | 53 | 70.31% | 95.74% | 82.81% | 8 | 9 | 2 | NA | 1x Shield Frame damage 1x Cpacitor Offset | 6th Sept 2024 | 14th Sept 2024 | 100% |  | PV1 | TAPTI
14 | T-GB-202437001 | GLOVE BOX | 1 | 300 | 400 | 340 | 96.5% | 88% | 85% | 169 | 14 | 46 | ICT - 11 Short/ Failure AXI - 3 BGA Short | TLA - MES, Testing Failure - 137 | 6th Sept 2024 | 1st October 2024 | 200% | Customer Visit and TQP documents approval dalyed. | TQP | TAPTI
15 | T-GB-202439001 | GLOVE BOX | 1 |  | 200 | 170 | 93% | 90.58% | 85% |  | 14 | 16 | ICT - 3 Failure Laser - 1 Offset Excess Solder - 10 SPI |  | 28th Sept 2024 | 1st October 2024 | 200% |  | TQP | TAPTI
16 | T-VC-202437001 | VC USB | 1 | 95 | 300 | 269 | 96.67% | 92.75% | 89.67% | 36 | 10 | 21 | NA | NA | 6th Sept 2024 | 9th October 2024 | 200% | ICT Tester had some relay issues, Then later repaired. | TQP | TAPTI
17 | T-BM-202438101 | BMB-Model 1 | 1 | 8 | 27 | 27 | 100% | NA | 100% | 19 | 0 | 0 | 3 Boards AOI Kapp 3 Boards AXI 10 Boards for Gauge R&R 3 Boards for Conformal Coating | NA | 18th Sept 2024 | 23rd Sept 2024 | 100% |  | TQP 2 | TAPTI
18 | T-BM-202438201 | BMB-Model 2 | 1 | 8 | 27 | 27 | 100% | NA | 100% | 19 | 0 | 0 |  | NA | 18th Sept 2024 | 23rd Sept 2024 | 100% |  | TQP 2 | TML
19 | T-BM-202438301 | BMB-Model 3 | 1 | 8 | 27 | 27 | 100% | NA | 100% | 19 | 0 | 0 |  | NA | 18th Sept 2024 | 23rd Sept 2024 | 100% |  | TQP 2 | TML
20 | T-BM-202438401 | BMB-Model 4 | 1 | 8 | 27 | 27 | 100% | NA | 100% | 19 | 0 | 0 |  | NA | 18th Sept 2024 | 23rd Sept 2024 | 100% |  | TQP 2 | TAPTI
21 | T-BM-202439101 | BMB-Model 1 | 1 | 5 | 75 | 73 | 97.33% | NA | 97.33% | 0 | 2 | 0 | NA | NA | 24th SEPT 2024 | 30th Sept 2024 | 100% |  | PILOT | TAPTI
22 | T-BM-202439201 | BMB-Model 2 | 1 | 5 | 75 | 71 | 94.67% | NA | 94.67% | 0 | 4 | 0 | NA | NA | 24th SEPT 2024 | 30th Sept 2024 | 100% |  | PILOT | TAPTI
23 | T-BM-202439301 | BMB-Model 3 | 1 | 5 | 75 | 75 | 100% | NA | 100% | 0 | 0 | 0 | NA | NA | 24th SEPT 2024 | 30th Sept 2024 | 100% |  | PILOT | TAPTI
24 | T-BM-202439401 | BMB-Model 4 | 1 | 5 | 75 | 75 | 100% | NA | 100% | 0 | 0 | 0 | NA | NA | 24th SEPT 2024 | 30th Sept 2024 | 100% |  | PILOT | TAPTI
25 | TM-M-202439001 | BMS MASTER | 1 | 23 | 23 | 23 | 100% | NA | 100% | 0 | 0 | 0 | NA | NA | 4th October 2024 |  |  |  | NPI | TAPTI
26 | TM-S-202439001 | BMS SLAVE | 1 | 26 | 26 | 26 | 100% | NA | 100% | 0 | 0 | 0 | NA | NA | 4th October 2024 |  |  |  | NPI | TAPTI
27 | T-UD-202440001 | USB DUO | 1 | 926 | 972 | 897 | 92.28% | NA | 92.28% | 0 | 75 | 0 | 18x Board broken 18x AOI KAPPA 5x Bridging - AOI 6x pick drop - AOI 23x Solder bridging - AXI 5x Excess void | 0 | 4th October 2024 |  |  |  | TQP | TAPTI
28 | T-VC-202444001 | VCUSB | 1 | 95 | [14 empty] | PV1.5 | TAPTI
29 | JL-GD-202445001 | GATE DRIVER | 1 | 10 | [14 empty] | NPI Testing | TAPTI
30 | T-VC-202446001 | VCUSB | 1 | 24 | [14 empty] | PV1.5 | TAPTI
31 | T-UD-202440001 | USB DUO | 1 | 926 | 972 | 897 | 92.28% | NA | 92.28% | 0 | 75 | 0 | 18x Board broken 18x AOI KAPPA 5x Bridging - AOI 6x pick drop - AOI 23x Solder bridging - AXI 5x Excess void | 0 |  |  |  |  | TQP | TAPTI
32 | T-VC-202444001 | VCUSB | 1 | 95 | 216 | 122 | 62.96% | 89.71% | 56.48% | [9 empty] | PV1.5 | TAPTI
33 | JL-GD-202445001 | GATE DRIVER | 1 | 10 | NA | NA | NA | NA | 100% | [9 empty] | NPI Testing | TAPTI
34 | T-VC-202446001 | VCUSB | 1 | 24 | 64 | 55 | 92.19% | 93.22% | 85.94% | [9 empty] | PV1.5 | TAPTI
35 | T-UD-202448001 | USB DUO | 2 | 34 | 54 | 51 | 94.44% | NA | 94.44% |  | 3 | [7 empty] | PV2 | TAPTI
36 | T-GB-202449001 | Glove Box | 2 | 44 | 60 | 46 | 78.33% | 97.87% | 76.67% |  | 13 | 1 | 9x SMT AOI/AXI reject 4x ICT Reject |  | 2nd December 2024 | 10th December 2025 |  |  | PV2 | TAPTI
37 | T-VC-202451001 | VC USB | 1 | 34 | 34 | 32 | 94.12% | 100% | 94.12% |  | 2 |  |  |  | 12th December 2024 | NOT COMPLETED |  |  | PV2 | TAPTI
38 | T-UD-202448001 | USB DUO | 2 | 36 | 34 | 22 | 64.71% | 64.71% | 41.87% |  | 12 |  | 9X Solder Birdging 4X EOL Failure, Connector open, Lift up. | [5 empty] | PV 3 | TAPTI
39 | T-GB-202449001 | Glove Box | 2 | 46 | 60 | LOT SCRAPPERD- WRONG COMPONENT PLACMENT |  |  |  |  | 60 | 1 | [5 empty] | LOT SCRAPPED | PV 3 | TAPTI
40 | T-VC-202509001 | VCUSB | 1 | 110 | 200 |  | 85% | 96.47% | 82% |  | 30 | 6 | 25x ICT Failure 5x AXI NG | 4x Gasket placement failure 2x Screwing station NG | 20th February 2025 | 7th March 2025
41 | T-GB-202509001 | GLOVEBOX | 1 | 110 | 200 |  | 99.5% | 99.5% | 99% |  | 1 | 1 | Pick and Place Component Liftup | Cable damage | 20th February 2025 | 7th March 2025
42 | T-UD-202510001 | USB DUO | 2 | 29 | 36 | 32 | 88.89% | 100% | 88.89% |  | 4 |  | 4 x Connector fall down. |  | 2025-03-19 | 2025-03-19 |  |  | PV3 | TAPTI
43
44
45

## NOMENCLETURE
| Name | Code
1 | GloveBox | T-GB-YYYYWW0xx
2 | USB Duo | T-UD-YYYYWW0xx
3 | VC USB | T-VC-YYYYWW0xx | T - Tapti | YYYY- Year | WW- Work Week | 0xx- Serial Number
4 | Audio Amplifier | T-AA-YYYYWW0xx | TE-TEJAS |  |  | a has 4 models
5 | BMB | T-BM-YYYYWWaxx | TM-TML |  |  |  | 1 | 1915616-01-B
6 | LNA | TE-LN-YYYYWW0xx | JL-JLR |  |  |  | 2 | 1915617-01-B
7 | TML -M | TM-M-YYYYWW0xx |  |  |  |  | 3 | 1915618-01-B
8 | TML -S | TM-S-YYYYWW0xx |  |  |  |  | 4 | 1915619-01-B
9 | Gate Driver | JL-GD-YYYYWW0xx
10
01 - Glovebox
02 - USB Duo
03 - VC USB